# Chapter 1

# Case Study, Agile Leadership Scenario Activity

Scenario: You are the athletic director, acting as the Scrum Master, responsible for guiding your NCAA Division I athletic department staff through a recent, unexpected change.

You received confirmation on a Monday morning that the upcoming women’s basketball game on Saturday has been selected for national television due to changes in conference standings. The game time is adjusted, media exposure will be significant, and attendance is expected to increase dramatically.

In your role, you will need to be prepared to maintain safety, optimize the fan experience, and ensure broadcast readiness.

Your task for this exercise is to arrange the following Scrum processes in the correct order they should occur to demonstrate effective agile leadership.

(Note to HK—The processes below are in the correct order. They need to be rearranged out of order for the student learning activity).

Assign scrum roles.

Conduct a sprint planning meeting.

Define the sprint goal.

Identify and prioritize the sprint process log.

Visualize the work using a scrum planning board.

Empower operational teams to self-organize and plan.

Hold daily stand-up meetings.

Remove impediments and make rapid decisions.

Conduct a final readiness check before the event.

Conduct a “hotwash” or after-action review.